## make it a little more detailed
Phase | Task | Start Date | End Date | Duration | Dependencies
Project Initiation | Project Kickoff & Planning | 2024-03-01 | 2024-03-07 | 1 week
| Requirements Gathering & Analysis | 2024-03-08 | 2024-03-22 | 2 weeks | Project Kickoff & Planning
| Project Charter & Documentation | 2024-03-23 | 2024-04-05 | 2 weeks | Requirements Gathering & Analysis
Design & Development | UI/UX Design & Prototyping | 2024-04-06 | 2024-05-10 | 5 weeks | Project Charter & Documentation
| Frontend Development | 2024-05-11 | 2024-06-28 | 7 weeks | UI/UX Design & Prototyping
| Backend Development & Database | 2024-05-11 | 2024-07-12 | 9 weeks | UI/UX Design & Prototyping
| Course Creation Tools Development | 2024-05-25 | 2024-07-26 | 9 weeks | UI/UX Design & Prototyping
| Learner Management System Development | 2024-06-01 | 2024-08-02 | 9 weeks | UI/UX Design & Prototyping
| Payment Gateway Integration | 2024-07-13 | 2024-08-16 | 5 weeks | Backend Development & Database
| Integration & System Testing | 2024-08-03 | 2024-09-13 | 6 weeks | Frontend Development, Backend Development & Database, Course Creation Tools Development, Learner Management System Development, Payment Gateway Integration
Testing & Launch | Beta Testing & User Feedback | 2024-09-14 | 2024-10-18 | 5 weeks | Integration & System Testing
| Final Bug Fixes & Refinement | 2024-10-19 | 2024-10-31 | 2 weeks | Beta Testing & User Feedback
| Deployment & Launch | 2024-11-01 | 2024-11-01 | 1 day | Final Bug Fixes & Refinement
Post-Launch | Post-Launch Review & Analysis | 2024-11-02 | 2024-11-30 | 4 weeks | Deployment & Launch
| Ongoing Maintenance & Updates | 2024-12-01 | Ongoing |  | Deployment & Launch